## pérenchies - charpent
PÉRENCHIES - Charpente Brisis
Planning
Name | Owner | Status | Priority | Timeline - Start | Timeline - End | Dependent On | Duration | Planned Effort | Effort Spent | Budget | Completion Date | link to JLM CHANTIERS
Task 1 | Julien LAMBOROT | Done | Low | 2025-03-16 | 2025-03-22 |  | 7 | 12 | 8 | 10000 | 2025-03-02 | PÉRENCHIES - Charpente Brisis
Task 2 |  | Working on it | Medium | 2025-04-01 | 2025-04-15 | Task 1 | 15 | 22 | 20 | 2000 |  | PÉRENCHIES - Charpente Brisis
Task 3 | [11 empty] | PÉRENCHIES - Charpente Brisis
|  |  |  | 2025-03-16 | 2025-04-15 | [5 empty] | 2025-03-02
Execution
Name | Owner | Status | Priority | Timeline - Start | Timeline - End | Dependent On | Duration | Planned Effort | Effort Spent | Budget | Completion Date | link to JLM CHANTIERS
Launch
Name | Owner | Status | Priority | Timeline - Start | Timeline - End | Dependent On | Duration | Planned Effort | Effort Spent | Budget | Completion Date | link to JLM CHANTIERS